AGILE PROJECT PLANNING REPORT

UNIT 2 — Agile Mini-Project

Course / Subject: [DevOps & Cloud]

Date: [6/9/2026]

# 1. Introduction

This document presents the complete Agile planning documentation for the Student Record and Academic Management Platform, developed as part of the Unit 2 Agile Mini-Project. Building on the Product Discovery work completed in Unit 1 — including the Product Vision Statement, Mission Statement, stakeholder analysis, business and functional requirements, user personas, MVP definition, and product roadmap — this report translates that foundation into actionable Agile deliverables using the Scrum framework.

The Student Record and Academic Management Platform is intended to help educational institutions manage student records, attendance, academic performance, course registration, and reporting through a secure, scalable, web-based application. The sections that follow define the Agile Product Vision, Scrum team structure, project Epics, User Stories, Acceptance Criteria, Product Backlog, Story Point estimates, Sprint plans, Scrum Board, Burndown Chart, simulated Scrum ceremonies, and a comparative study of Agile frameworks.

## 1.1 Purpose of This Document

- Provide a single reference for how the project will be planned and executed using Scrum.

- Demonstrate traceability from business requirements through Epics, User Stories, and Sprints.

- Define roles, responsibilities, and ceremonies for the Scrum Team.

- Establish a prioritized, estimated Product Backlog and an initial release plan.

## 1.2 Recap of Unit 1 Product Discovery Inputs

- Product Vision Statement and Mission Statement reviewed and carried forward.

- Stakeholders identified: Students, Faculty, Academic Administrators, IT Administrators, Institution Management.

- Business Requirements: centralize student data, digitize attendance and marks, enable role-based reporting.

- Functional Requirements: student registration, course management, attendance tracking, marks entry, notifications, reporting.

- Non-functional Requirements: security, data privacy, scalability, availability, usability, performance.

- User Personas: Student, Faculty Member, Academic Administrator, IT Administrator.

- MVP: authentication, student registration/search, course management, attendance recording, and basic reporting.

- Product Roadmap: phased delivery from core records management to advanced analytics and notifications.

# 2. Product Vision Document

## 2.1 Agile Product Vision Statement

“Develop a secure and user-friendly Student Record and Academic Management Platform that enables educational institutions to efficiently manage student records, attendance, academic performance, course registration, and reporting through a scalable web-based application.”

## 2.2 Overall Product Objective

To replace fragmented, manual, and paper-based student administration processes with a unified digital platform that improves accuracy, transparency, and accessibility of academic data for all stakeholders.

## 2.3 Primary Users of the System

- Students — view profile, attendance, marks, and results.

- Faculty Members — record attendance, enter marks, view course rosters.

- Academic Administrators — manage courses, oversee reporting, configure the academic calendar.

- IT Administrators — manage user accounts, roles, and system security.

## 2.4 Business Benefits

- Reduced administrative overhead through automation of records and reporting.

- Improved data accuracy and reduced duplication of student information.

- Faster turnaround on attendance and result generation.

- Better decision-making through consolidated academic analytics.

- Improved communication via automated notifications and alerts.

## 2.5 Measurable Success Criteria

- 95% of attendance entries completed digitally within one academic term of rollout.

- Result sheet generation time reduced from days to minutes.

- Zero critical security incidents related to unauthorized data access.

- System availability of 99.5% during academic hours.

- At least 90% user satisfaction score from faculty and student surveys post-launch.

## 2.6 Project Constraints

- Fixed academic-term timeline for MVP rollout.

- Limited development team size (single Scrum Team for the mini-project).

- Must comply with institutional data privacy and security policies.

- Web-based delivery only for the initial release; mobile app out of scope for MVP.

## 2.7 Expected Software Capabilities

- Secure authentication with role-based access control.

- Student registration, profile management, and search.

- Course creation, updates, and student assignment.

- Digital attendance recording and reporting.

- Marks entry, grade calculation, and result sheet generation.

- Automated notifications for attendance, exams, and results.

- Consolidated reporting across students, courses, attendance, and performance.

# 3. Scrum Team Structure

The project is delivered by a single, self-organizing Scrum Team responsible for all planning, design, development, testing, and delivery activities for the Student Record and Academic Management Platform.

| Role | Name / Assignment | Team Size |
| --- | --- | --- |
| Product Owner | [Aditi Asane] | 1 |
| Scrum Master | [Anushka Rajdev] | 1 |
| Development Team | [Ruhanshi,Rushikesh,Aarvi,Ayesha,Vanshika] | 5 |

# 4. Scrum Roles and Responsibilities

## 4.1 Product Owner

- Defining product requirements in collaboration with stakeholders.

- Prioritizing and continuously refining the Product Backlog.

- Representing stakeholder interests throughout the project.

- Reviewing and accepting completed work at the end of each Sprint.

## 4.2 Scrum Master

- Facilitating Scrum ceremonies: Sprint Planning, Daily Scrum, Sprint Review, Retrospective.

- Identifying and removing impediments that block the team's progress.

- Ensuring the team follows Agile and Scrum practices consistently.

- Coaching the team on self-organization and continuous improvement.

## 4.3 Development Team

- Designing the application architecture and user interface.

- Writing, reviewing, and integrating code for committed User Stories.

- Testing software to meet Acceptance Criteria and Definition of Done.

- Preparing supporting technical and user documentation.

- Demonstrating completed features during Sprint Review.

# 5. Epic Documentation

The complete application is organized into seven high-level functional modules (Epics). Each Epic groups related features and will be progressively broken down into User Stories for Sprint delivery.

## Epic 1 — Student Management

Purpose and Scope:

Enable complete lifecycle management of student records, from registration through profile updates and search, forming the core data foundation of the platform.

Features:

- Student Registration

- Student Profile Management

- Student Search

- Student Update

- Student Deletion

## Epic 2 — Course Management

Purpose and Scope:

Allow administrators to create and maintain course offerings and assign students to the correct courses each academic term.

Features:

- Add Course

- Update Course

- Assign Students

- View Course Details

## Epic 3 — Attendance Management

Purpose and Scope:

Digitize the recording, viewing, and reporting of student attendance to replace manual attendance registers.

Features:

- Record Attendance

- View Attendance

- Attendance Reports

## Epic 4 — Marks and Academic Performance

Purpose and Scope:

Provide faculty the ability to enter and update marks, automatically calculate grades, and generate result sheets.

Features:

- Enter Marks

- Update Marks

- Calculate Grades

- Generate Result Sheets

## Epic 5 — Authentication and Security

Purpose and Scope:

Ensure only authorized users can access the platform and that access is appropriately scoped by role.

Features:

- User Login

- Logout

- Password Reset

- Role-Based Access Control

## Epic 6 — Notifications

Purpose and Scope:

Keep students and faculty informed through timely automated alerts for attendance, examinations, and results.

Features:

- Attendance Alerts

- Examination Notifications

- Result Notifications

## Epic 7 — Reporting

Purpose and Scope:

Provide consolidated, exportable reports across students, attendance, performance, and courses to support decision-making.

Features:

- Student Reports

- Attendance Reports

- Performance Reports

- Course Reports

# 6. User Story Repository

Every Epic has been broken down into User Stories using the standard Agile format: “As a <role>, I want to <goal> so that <benefit>.” Acceptance Criteria are defined alongside each story to establish a clear Definition of Done, satisfying both the User Story Repository and Acceptance Criteria Document deliverables.

## Epic 1 – Student Management

As a Academic Administrator, I want to register a new student so that the student's records exist in the system for enrollment.

Priority: High   |   Story Points: 3

Acceptance Criteria:

  - Admin can enter student personal and academic details.

  - Mandatory fields are validated before submission.

  - A unique Student ID is generated automatically.

  - Registration confirmation is displayed on success.

As a Academic Administrator, I want to search for a student by name or ID so that I can quickly locate and manage their record.

Priority: High   |   Story Points: 2

Acceptance Criteria:

  - Search returns matching results in real time.

  - Search supports partial name matches.

  - No-match cases show a clear empty state.

  - Search results link to the full student profile.

As a Academic Administrator, I want to update a student's profile so that records remain accurate over time.

Priority: Medium   |   Story Points: 3

Acceptance Criteria:

  - Existing details are pre-filled in the edit form.

  - Changes are validated before saving.

  - Updated data is reflected immediately after save.

  - An audit trail records who made the change.

## Epic 2 – Course Management

As a Academic Administrator, I want to add a new course so that it becomes available for student assignment.

Priority: Medium   |   Story Points: 2

Acceptance Criteria:

  - Admin can enter course code, name, credits, and faculty.

  - Duplicate course codes are rejected.

  - New course appears in the course list immediately.

  - Confirmation message is shown on success.

As a Academic Administrator, I want to assign students to a course so that enrollment records are accurate for the term.

Priority: Medium   |   Story Points: 3

Acceptance Criteria:

  - Admin can select one or multiple students to assign.

  - Already-assigned students are indicated.

  - Assignment is reflected in the student's profile.

  - Course roster count updates automatically.

## Epic 3 – Attendance Management

As a Faculty Member, I want to record student attendance so that attendance records remain accurate and updated.

Priority: High   |   Story Points: 3

Acceptance Criteria:

  - Faculty can select a course.

  - Faculty can select a lecture date.

  - Faculty can mark attendance.

  - Attendance records are saved successfully.

  - Attendance reports can be generated.

As a Student, I want to view my attendance record so that I can track my attendance percentage.

Priority: Medium   |   Story Points: 2

Acceptance Criteria:

  - Student can view attendance by course.

  - Overall attendance percentage is displayed.

  - Records update after each lecture is marked.

  - Low-attendance status is visually flagged.

## Epic 4 – Marks and Academic Performance

As a Faculty Member, I want to enter marks for a course so that student performance is recorded accurately.

Priority: High   |   Story Points: 5

Acceptance Criteria:

  - Faculty can enter marks per student per assessment.

  - Marks outside the valid range are rejected.

  - Entered marks are saved and time-stamped.

  - Only the assigned faculty can enter marks for a course.

As a System, I want to automatically calculate grades so that results are consistent and free of manual error.

Priority: Medium   |   Story Points: 5

Acceptance Criteria:

  - Grades are computed from a configurable grading scale.

  - Calculation runs automatically once all marks are entered.

  - Calculated grades can be reviewed before publishing.

  - Any recalculation is logged.

As a Academic Administrator, I want to generate result sheets so that official results can be shared with students and records.

Priority: Medium   |   Story Points: 5

Acceptance Criteria:

  - Result sheets can be generated per student or per course.

  - Sheets include subject-wise marks and final grade.

  - Sheets can be exported as PDF.

  - Only finalized marks appear on the result sheet.

## Epic 5 – Authentication and Security

As a Registered User, I want to log in to the platform so that I can securely access features relevant to my role.

Priority: High   |   Story Points: 2

Acceptance Criteria:

  - Login page loads successfully.

  - Registered users can log in.

  - Invalid credentials display appropriate error messages.

  - Successful login redirects to the dashboard.

  - Session management functions correctly.

As a Registered User, I want to reset my password so that I can regain access if I forget my credentials.

Priority: Medium   |   Story Points: 3

Acceptance Criteria:

  - User can request a reset link via registered email.

  - Reset link expires after a defined time window.

  - New password must meet complexity rules.

  - User is notified on successful reset.

As a IT Administrator, I want to configure role-based access control so that users only see features appropriate to their role.

Priority: High   |   Story Points: 5

Acceptance Criteria:

  - Roles (Student, Faculty, Admin) map to defined permission sets.

  - Unauthorized actions are blocked with a clear message.

  - Role changes take effect without requiring re-registration.

  - Access attempts are logged for audit.

## Epic 6 – Notifications

As a Student, I want to receive an attendance alert so that I am aware when my attendance falls below the required threshold.

Priority: Medium   |   Story Points: 3

Acceptance Criteria:

  - Alert triggers automatically when attendance drops below the set threshold.

  - Alert is delivered via the platform and/or email.

  - Alert includes current attendance percentage.

  - Duplicate alerts are not sent for the same threshold breach.

As a Student, I want to receive examination and result notifications so that I stay informed about important academic dates and outcomes.

Priority: Low   |   Story Points: 2

Acceptance Criteria:

  - Notification is sent when an exam is scheduled.

  - Notification is sent when results are published.

  - Notifications appear in an in-app notification center.

  - Users can mark notifications as read.

## Epic 7 – Reporting

As a Academic Administrator, I want to generate consolidated attendance and performance reports so that I can support institutional decision-making.

Priority: Medium   |   Story Points: 5

Acceptance Criteria:

  - Reports can be filtered by course, term, and student.

  - Reports can be exported as PDF or CSV.

  - Report data matches underlying attendance and marks records.

  - Report generation completes within an acceptable time.

# 7. Acceptance Criteria Document — Summary

Acceptance Criteria for every User Story are documented in Section 6 alongside each story so that criteria stay directly traceable to the story they define. As a representative example, the Acceptance Criteria for the Student Login story are highlighted below, since it defines the platform's baseline Definition of “Done” for access.

## Example — Student Login

- Login page loads successfully.

- Registered users can log in.

- Invalid credentials display appropriate error messages.

- Successful login redirects to the dashboard.

- Session management functions correctly.

Students should treat Acceptance Criteria as testable, measurable conditions — not vague statements — so that the Development Team and Product Owner share a common understanding of when a story is complete.

# 8. Prioritized Product Backlog

All User Stories are consolidated into a single Product Backlog and prioritized based on business value, user importance, technical dependencies, and implementation complexity. The Product Owner maintains and re-prioritizes this backlog throughout the project.

| Priority | Epic | User Story | Story Points |
| --- | --- | --- | --- |
| High | Authentication and Security | User Login | 2 |
| High | Student Management | Register Student | 3 |
| High | Student Management | Search Student | 2 |
| High | Attendance Management | Record Attendance | 3 |
| High | Authentication and Security | Role-Based Access Control | 5 |
| Medium | Course Management | Add Course | 2 |
| Medium | Course Management | Assign Students | 3 |
| Medium | Student Management | Update Student Profile | 3 |
| Medium | Marks and Academic Performance | Enter Marks | 5 |
| Medium | Marks and Academic Performance | Calculate Grades | 5 |
| Medium | Marks and Academic Performance | Generate Result Sheets | 5 |
| Medium | Authentication and Security | Password Reset | 3 |
| Medium | Attendance Management | View Attendance | 2 |
| Medium | Notifications | Attendance Alert | 3 |
| Medium | Reporting | Attendance and Performance Reports | 5 |
| Low | Notifications | Examination and Result Notifications | 2 |

This ordering supports incremental delivery: authentication and core student/attendance capabilities are delivered first, followed by course and academic performance features, with notifications and advanced reporting following in later Sprints.

# 9. Story Point Estimation Sheet

The Development Team estimated effort for each User Story using Story Points via collaborative Planning Poker sessions. The Fibonacci-like scale below was used consistently across all estimation sessions.

| Story Points | Complexity |
| --- | --- |
| 1 | Very Easy |
| 2 | Easy |
| 3 | Moderate |
| 5 | Difficult |
| 8 | Very Difficult |
| 13 | Highly Complex |

## Estimation Summary by Epic

| Epic | Total Story Points |
| --- | --- |
| Student Management | 8 |
| Course Management | 5 |
| Attendance Management | 5 |
| Marks and Academic Performance | 15 |
| Authentication and Security | 10 |
| Notifications | 5 |
| Reporting | 5 |

Total estimated Product Backlog effort: 53 Story Points across all documented stories.

# 10. Sprint Planning Document

The Product Backlog is organized into three initial two-week Sprints. Each Sprint has a defined Sprint Goal, a Sprint Backlog of committed stories, and expected deliverables.

## Sprint 1

Sprint Goal: Develop user authentication and project setup.

Sprint Backlog:

- Repository initialization

- User registration

- Login functionality

- Basic user interface

- Testing

Expected Deliverable: A working, tested login/authentication flow and initial project scaffold ready for feature development.

## Sprint 2

Sprint Goal: Develop the Student Management Module.

Sprint Backlog:

- Add Student

- Search Student

- Update Student

- Delete Student

Expected Deliverable: A fully functional Student Management module integrated with authentication and role-based access.

## Sprint 3

Sprint Goal: Develop Course and Attendance Management.

Sprint Backlog:

- Add Course

- Assign Courses

- Record Attendance

- Attendance Reports

Expected Deliverable: Course setup, student-course assignment, and end-to-end attendance recording and reporting.

# 11. Sprint Backlog — Sprint 1 Detail

The table below shows the Sprint 1 backlog broken into tasks with estimated effort and ownership, as tracked by the team during Sprint execution.

| Task | Owner | Description | Est. Hours | Status |
| --- | --- | --- | --- | --- |
| Repository initialization | Dev Team | Set up source control, CI, and project skeleton | 4 | Done |
| User registration | Dev Team | Build registration form and backend endpoint | 8 | Done |
| Login functionality | Dev Team | Implement authentication and session handling | 10 | Done |
| Basic user interface | Dev Team | Build shared layout, navigation, and styling | 8 | In Progress |
| Testing | Dev Team | Unit and integration tests for auth flow | 6 | In Progress |

# 12. Scrum Board

The team maintains a Scrum Board (physical or digital, e.g. Trello/Jira) throughout each Sprint to visualize progress. A snapshot from mid-Sprint 1 is shown below.

| Backlog | To Do | In Progress | Testing | Completed |
| --- | --- | --- | --- | --- |
| Course | Add Student | Basic UI | — | Repository Setup |
| Attendance | Attendance Alerts | Testing (Auth) | — | User Registration |
| Marks Entry | — | — | — | Login Functionality |

The board is updated daily by team members during the Daily Scrum so that progress and blockers remain visible to the whole team.

# 13. Burndown Chart

The Sprint 1 Burndown Chart below tracks remaining Story Points against the ideal completion line across the 10-day Sprint. The team trended slightly behind the ideal line mid-Sprint due to onboarding overhead but converged by Sprint end.

# 14. Sprint Review Report

Sprint: Sprint 1 — User Authentication and Project Setup

Attendees: Product Owner, Scrum Master, Development Team, [invited stakeholders]

## Features Demonstrated

- Working login and logout flow with session management.

- User registration form with validation.

- Initial shared application layout and navigation.

## Stakeholder Feedback

- Positive feedback on the clarity of the login and registration screens.

- Request to add password strength guidance during registration.

- Confirmation that role-based redirect behavior meets expectations.

## Product Backlog Adjustments

- Added a new story: display password strength indicator on registration.

- Re-confirmed Sprint 2 scope (Student Management Module) as previously planned.

# 15. Sprint Retrospective Report

Sprint: Sprint 1

## What Went Well

- Team collaborated effectively during Planning Poker to reach estimation consensus.

- Daily Scrums stayed focused and within the 15-minute timebox.

- Repository and CI setup completed ahead of schedule.

## What Challenges Occurred

- Underestimated the effort required for session management edge cases.

- Some ambiguity in Acceptance Criteria for the login story required mid-Sprint clarification.

## Improvements for Next Sprint

- Review Acceptance Criteria for ambiguity during Sprint Planning, before Sprint start.

- Add a technical spike task for any story with unclear technical risk.

- Continue daily Scrum Board updates to keep blockers visible early.

# 16. Agile Framework Comparison Report

A comparative study of the Agile frameworks introduced in the syllabus was conducted to select the most suitable approach for this project.

| Framework | Best Fit Context | Strengths | Limitations |
| --- | --- | --- | --- |
| Scrum | Small, cross-functional teams; fixed-length Sprints | Clear roles and ceremonies; strong at managing changing requirements | Can struggle to scale across multiple teams without extra coordination |
| Kanban | Continuous flow work with visual boards | Simple to adopt; excellent for support/maintenance-style work | No built-in cadence for planning or review; less structure for a fixed-scope project |
| Extreme Programming (XP) | Engineering-heavy teams needing high code quality | Strong technical practices: pair programming, TDD, continuous integration | Demanding discipline; less focus on broader project/product management |
| Lean Development | Teams focused on eliminating waste and maximizing value flow | Encourages efficiency and continuous improvement | Fewer prescriptive practices; needs pairing with a framework like Scrum or Kanban |
| Large Scale Scrum (LeSS) | Multiple Scrum Teams working on one product | Extends Scrum principles with minimal added process | Overhead not justified for a single-team mini-project |
| Scaled Agile Framework (SAFe) | Large enterprises with many teams and programs | Strong alignment across large organizations and portfolios | Heavyweight and process-intensive for a small, single-team project |
| Scrum@Scale | Multiple Scrum Teams needing scaled coordination | Modular scaling built directly on standard Scrum | Added coordination roles unnecessary at small scale |

## Recommendation

Scrum is recommended for the Student Record and Academic Management Platform. The project is delivered by a single team over a fixed academic-term timeline with evolving requirements across clearly separable modules (Epics) — conditions where Scrum's fixed Sprints, defined roles, and regular inspect-and-adapt ceremonies (Sprint Review, Retrospective) provide the right balance of structure and flexibility. Frameworks such as LeSS, SAFe, and Scrum@Scale add coordination overhead intended for multiple teams, which is unnecessary at this project's scale, while Kanban and XP alone lack the planning cadence and role structure the team needs for a project with defined Sprint deliverables and stakeholder reviews.

# 17. Project Timeline and Release Roadmap

| Sprint | Duration | Focus | Release Milestone |
| --- | --- | --- | --- |
| Sprint 1 | Weeks 1–2 | Authentication and project setup | Internal build — login functional |
| Sprint 2 | Weeks 3–4 | Student Management Module | Alpha release — student records manageable |
| Sprint 3 | Weeks 5–6 | Course and Attendance Management | Beta release — attendance workflow live |
| Sprint 4 (planned) | Weeks 7–8 | Marks, grading, and result sheets | Release Candidate — academic performance module |
| Sprint 5 (planned) | Weeks 9–10 | Notifications and reporting | MVP Release — full MVP scope complete |

This roadmap reflects the sequencing defined in the Prioritized Product Backlog: security and core student data first, followed by course/attendance workflows, then academic performance, and finally notifications and reporting — culminating in the full MVP release described in the Unit 1 Product Roadmap.

# 18. Deliverables Checklist

This single report satisfies every deliverable required at the end of Unit 2:

| # | Deliverable | Covered In | Status |
| --- | --- | --- | --- |
| 1 | Agile Project Planning Report | Section 1 | Complete |
| 2 | Product Vision Document | Section 2 | Complete |
| 3 | Scrum Team Structure | Section 3 | Complete |
| 4 | Scrum Roles and Responsibilities Document | Section 4 | Complete |
| 5 | Epic Documentation | Section 5 | Complete |
| 6 | User Story Repository | Section 6 | Complete |
| 7 | Acceptance Criteria Document | Section 7 | Complete |
| 8 | Prioritized Product Backlog | Section 8 | Complete |
| 9 | Story Point Estimation Sheet | Section 9 | Complete |
| 10 | Sprint Planning Document | Section 10 | Complete |
| 11 | Sprint Backlog | Section 11 | Complete |
| 12 | Scrum Board | Section 12 | Complete |
| 13 | Burndown Chart | Section 13 | Complete |
| 14 | Sprint Review Report | Section 14 | Complete |
| 15 | Sprint Retrospective Report | Section 15 | Complete |
| 16 | Agile Framework Comparison Report | Section 16 | Complete |
| 17 | Project Timeline and Release Roadmap | Section 17 | Complete |
| 18 | Complete Agile Documentation for the Platform | This entire document | Complete |

# 19. Conclusion

Through this Unit 2 Agile Mini-Project, the Scrum Team translated the Unit 1 Product Discovery outputs for the Student Record and Academic Management Platform into a complete, actionable Agile plan. The team defined the Agile Product Vision, organized Scrum roles, decomposed the product into Epics and User Stories with clear Acceptance Criteria, built and estimated a prioritized Product Backlog, planned initial Sprints, and practiced core Scrum ceremonies. Combined with the Agile framework comparison confirming Scrum as the right fit, this documentation provides a solid foundation for moving into iterative development in Unit 3 and beyond.